## Sheet1
				effort, man-month
API	Equipment Model	Comment		no of devices		Linac	convert	replace?		Outlook	challenge
BCU	Unilac Chopper			2		X	0.25
CEHV	Switch of Electron Cooler			2				0.5		Use Exploder (WR-TIF)?
CS	Stochastic Cooling			1			2				many elements on byte-ports, partly ramped
DC	Strommessung Cup	only ion sources		9		X		0.5		option: use DCI/DTI HW
DCI	Integrale Pulsstrommessung Cup			67		X	0.25			new HW? Not yet planned
DGX	Profile Grid			190			2			many devices – keep?	time critical, multiplexer
DPB	Bunchgenerator			5		X				uses DPX
DPX	Phasensonde			37		X	1			established installation – keep?
DS	Stepping Motor			205			2			many devices – keep?	multiplexer, left/right configuraion
DSK	Collimator, see Stepping Motor	Properties only, uses DS					0.25			see DS
DSME	Motorsteuerung des Injektions-Septums			1			1.5			MicroIOC, but special handling
DTC	Trafos			6				0.5		adapt FAIR-HW, FESA ready
DTI	Integrale Pulsstrommessung Trafo			55		X		0.5		thoughts for HW-replacement
DTTC	Beamloss Monitor (High Current)			26		X		0.5		combine with DTI
DX	Beam Position Monitor					0.25			range setting phase-probes only
ESAU	E-Cooler Special Application Units			9			0.5
EZR	EZR RF	basiert auf STD		2		X				subset in STD
FBSD	Feedback Schottky Diagnose					probably no longer used
HFU	Unilac RF			36		X	1				time critical, pulse/pause handling
HFUM	HFU Medien			6		X		0.5		- > SILECS?
HSAU	HLI Special Application Units	basiert auf STD		20		X	0.5			subset in STD
IQX	Ion Source Power Supplies			49		X	0.5			subset in PowerSupply
ISAU	Ion Source Special Application Units	basiert auf STD		9		X				subset in STD
ISCP	Ion Source Current Peak	basiert auf STD		3		X				subset in STD
ISDP	Ion Source Cup	basiert auf STD		3		X				subset in STD
ISEE	Ion Source Extraction Electrodes	basiert auf STD		2		X				subset in STD
ISMO	Ion Source Motor Drive	basiert auf STD		5		X				subset in STD
ISRM	X-Ray Monitor	basiert auf STD		2		X				subset in STD
ISSD	Sputter Puls Super Device	basiert auf STD		2		X				subset in STD
ISSP	Sputter Puls	basiert auf STD		1		X				subset in STD
ISVT	Turbopump	basiert auf STD		12		X				subset in STD
MB	Bumper			5			2			replacement by FESA planed	closed-loop control, testing with device only
MBUK	Bunch Compressor	basiert auf STD					anyhow new SW (FESA)
MD	DC-Magnet					(x)	0.25			use PowerSupply
ME	Elektrostatic Septum			3			1			integrate in PowerSupply
MK	Kicker			3			3			single modules like SIS100?	complex device
MS	Sweeper			2		X	0.5			integrate in PowerSupply
MX	Pulsed Magnet	HSI Timing				(x)	2				time critical
MXS	Serial Connected Pulsed Magnet			2		X	0.5			handle in PowerSupply
PLA	Pressluftantriebe			367			0.5			many devices – keep?
PPOS	Positionierbarer PLA			9			1
RPG	Rahmenpulsgenerator			13				1		Use Exploder (WR-TIF)?
STD	Standard Devices					0.5			diff. Models: use subsets
STHV	Stepping HV			1				1.5		replace device?	rotating preloading of sub power supplies
TGX	Timing Generator Kicker					0.5
UG	Unilac Gasstripper			1		X	0.5			new device (pulsed)?

		number of eq-models					25	8
		effort for conversion to FESA (months)					24.25	5.5

will be obsolete
BC	SIS Injection Chopper	Kalibrierung von GTK7BC1L					new device, in FESA
DMAN	Device Manager	eq-model of GµP
DSM	Motor, controlled with uIOC					FESA-SW running
DSKM	Collimator controlled with uIOC					FESA-SW running
EC	Equipment Controller	eq-model of EC
IPS	Interactive Peripheral System	Poti-Board
PZU	PZ Unilac Eventverteilung					X				new white rabbit timing master
PZUA	PZ Unilac Alarmhandling					X
PZUI	PZ Unilac Interlock Choppersteuerung					X
PZUS	PZ Unilac Superzyklus					X
SWPZ	Software Timing Generator	software tests, ion source test facilities					not for accelerator operation
VVC	Vacuum Ventile	HW-responsible: VAC		158					SPS/UNICOS

No Longer Used
API	Equipment Model	Comment
PZS	PZ SIS/ESR Eventverteilung	Schema Synchronisierung SIS/ESR-Pulszentralen, replaced by FESA FAIR-TM
FG	Function Generator	replaced by FESA
HVDM	HV Power Supplies CAEN	replaced by FESA (new HW)
DI	Spill Counter	replaced by FESA
CE	Electron Cooler
DCV	Stromverlauf
DSI	Scraper Current
DTX	Beam Trafo (Slow and Fast)	replaced, new device with FESA
EMA	Emittance
HFS	HF Synchronisation	obsolet, new switch-matrix will use FESA
IT	Internal Target ESR
TFS	Transversal Feedback System
TG	Timing Generator SIS	replaced by TGX
DTP	Schnelle Strahltrafos Pulsform	never implemented