## Tabelle1
		Fr 28.06.24	Sa 29.06.24	So 30.06.24	Mo 01.07.24	Di 02.07.24	Mi 03.07.24	Do 04.07.24	Fr 05.07.24	Sa 06.07.24	So 07.07.24	Mo 08.07.24	Di 09.07.24	Mi 10.07.24	Do 11.07.24	Fr 12.07.24	Sa 13.07.24	So 14.07.24	Mo 15.07.24	Di 16.07.24	Mi 17.07.24	Do 18.07.24	Fr 19.07.24

	Dry Run Coordinator	Peter			Hanno	Peter	Peter	Hanno	Peter			Hanno	Peter	Peter	Hanno				Hanno	Peter	Peter	Hanno	Peter
	standby					Hanno		Peter				Peter	Hanno						Peter	Hanno		Peter
															Beamtime Retreat	Beamtime Retreat
	Machine state	Beam production UL-TK			front ends online, power stages off	front ends online, power stages off	front ends online, power stages off	front ends online, power stages off	front ends online, power stages off			front ends online, power stages off	front ends online, power stages off	front ends online, power stages off	front ends online, power stages off	front ends online, power stages off			front ends online, at least a few devices of each type switched on	front ends online, at least a few devices of each type switched on	front ends online, at least a few devices of each type switched on	front ends online, at least a few devices of each type switched on	front ends online, at least a few devices of each type switched on

	Shift	Early + Late			none	none	none	none	none			none	none	none	none	none			yes (RF)	yes (RF)	yes (RF)	yes (RF)	yes (RF)
	On-call	none			none	none	none	none	none			none	none	none	none	none			RF	RF	RF	RF	RF

Main tasks	Morning	TOS WR-MIL Gateway			APP LSA Rollout	APP test adapted DevAcc models	Legacy system test	TOS/HEL change timing system	TOS/HEL/LSA/BSS test timing system			TOS/HEL/LSA/BSS test timing system	TOS/HEL/LSA/BSS test timing system	check timing at front ends	check timing at front ends	test potiboard			Prepare RF commissioning	RF one bp chain + stabilizers	RF several bp chains + stabilizers + conditioners	test magnet high brho broadcast (HSI)
					SER Rollout	MOD Model/data supply tests		FEC/HEL change chopper control	FEC/HEL test chopper control			check 50Hz sync	PZU/DM comparison	test injection (timing only) into SIS18?	check SVÜ	Non-interruptive trims			RF commissioning		test magnet multiplexing	test magnet TK preparation
					FEC Rollout	LSA/BSS data master supply test			check 50Hz sync				Non-interruptive timing changes	test profile grid protection								test magnet TK magn down
					BEA Rollout?	APP test applications								test no beam (interlock/disable)								test magnet TK sweeper magnets?
					INN Update ACC6	INN Update ACC6

Main tasks	After / Noon	UNILAC Shutdown			APP LSA Smoke tests	APP test adapted DevAcc models	Legacy system test	TOS/HEL change timing system	TOS/HEL/LSA/BSS test timing system			TOS/HEL/LSA/BSS test timing system	TOS/HEL/LSA/BSS test timing system	check timing at front ends	check timing at front ends	test potiboard			RF test with simple super cycle, low amplitudes	RF several bp chains + stabilizers	RF stabilizers + conditioners without bp chains	test potiboard
		APP LSA Rollout			SER Smoke tests	Model/data supply tests		FEC/HEL change chopper control	FEC/HEL test chopper control				PZU/DM comparison		check SVÜ	Non-interruptive trims			RF one beam production chain at 50Hz	test magnet multiplexing
		SER Rollout				LSA/BSS data master supply test							Non-interruptive timing changes
					SER DevAcc nameserver	APP test applications
		FEC Rollout			INN Update ACC6	INN Update ACC6

Secondary tasks	APP					Test applications	Test applications	Test applications	Test applications
						Test applications wrt NONMUX		APP test adapted DevAcc models	APP test adapted DevAcc models
								Test applications wrt NONMUX
	FEC

	TOS

	LSA						LSA/BSS data master supply test	LSA/BSS data master supply test

	MOD							Model/data supply tests	Model/data supply tests
								Model/data supply tests NONMUX	Model/data supply tests NONMUX
	SER

						need at least 2 contexts resident for APP tests
					MASP: integrate all UNILAC devices	MASP: integrate all UNILAC devices	MASP: integrate all UNILAC devices	MASP: integrate all UNILAC devices	MASP: integrate all UNILAC devices

					MAPS testing	MAPS testing	MAPS testing	MAPS testing	MAPS testing			MAPS testing	MAPS testing	MAPS testing	MAPS testing	MAPS testing			MAPS testing	MAPS testing	MAPS testing	MAPS testing	MAPS testing